## Sheet1
S.no. | Product Backlog | Priority | Team Member | Time/Effort | Status | Sprint 1 (2 Weeks) | Sprint 2 (3 Weeks) | Sprint 3 (2 Weeks)
1 | Start Screen | 1 | Daniel | 1week | Complete | 1 week
2 | Software Engineering Ethics learn | 2 | Ben&Sai Ram | 1week | In-Progress |  | 1 week
3 | Level Select Screen | 3 | Sai Ram&Neeharika | 1week | Complete | 1 week
4 | Mini Game 1 | 5 | Ben&Daniel | .5week | In-Progress |  | .5 week
5 | Mini Game 2 | 5 | Neeharika&Sai Ram | .5week | Complete |  | .5 week
6 | Mini Game 3 | 5 | Ben&Neeharika | .5week | Incomplete |  |  | .5 week
7 | Questionare/Database | 3 | Daniel&Neeharika | 1week | Incomplete |  |  | 1 week
8 | Exit Screen | 3 | Sai Ram&Daniel | 1week | Incomplete |  | 1 week
9 | Scores | 4 | Ben&Daniel | .5week | Incomplete |  |  | .5 week
10 | Wireframing | 2 | All | .25week | Incomplete |  |  | .25 week
11 | Educator Sign-in | 6 |  |  | Incomplete
12 | Save Game | 6 |  |  | Incomplete
13 | Educator Questionare Input | 6 |  |  | Incomplete
14 | Sign in/ Register | 6 |  |  | Incomplete